# Touch Grass — Master Plan · to November 28

## A 24-hour youth hackathon on health and the environment · 220+ participants

Prepared Wednesday October 7, 2026. Event Saturday November 28 to Sunday November 29.

## 1. Goals and what done looks like

On Sunday November 29 at 17:00:

- 200+ participants attended, 50+ teams submitted, nobody got hurt.

- Every submitted team demoed something that runs, to a judge who scored it.

- Five track winners and an overall top three announced on stage, prizes handed over.

- Five or six Platinum sponsors, five Gold track sponsors, and food covered by Silver sponsors or in kind; the prize pool funded above its 5,000,000 MNT floor.

- 25+ schools and universities represented.

By Friday December 4: 6. Results post with project links published; thank-yous sent; report with numbers, photos and the itemized ledger delivered to every sponsor and partner; survey closed; retro done; a date pencilled for 2027.

Metrics to record on the day: registrations, check-ins, overnight stayers, teams, submissions, finalists, schools and universities, mentors, judges, sponsors and amounts, photos taken, survey responses.

## 2. Decisions

Locked

| Decision | Value |
| --- | --- |
| Name | Touch Grass |
| Dates | Sat Nov 28 – Sun Nov 29, 2026 |
| Format | 24-hour hack, Sat 13:00 → Sun 13:00, overnight at the venue; Plan B daytime split if overnight refused |
| Scale | 220+ attending, plan for 260 registrations, cap 300 |
| Audience | ages 16–26: high school and university students, gap-year students and young builders; 45,000 MNT fee |
| Theme | broad, TreeHacks model: Healthcare, Sustainability, Education, Humanity, AI; no problem list |
| Organizers | Hackathon Mongolia, a student collective (GitHub org Hackathon-Mongolia, not a registered entity), runs the program; Uram Enerel NGO (Uram Care), registered and government-recognized, is the legal host |
| Legal host | Uram Enerel NGO: signs contracts, receives funds, pays vendors, issues e-barimt, reports |
| Recognition | through Uram Enerel: [government body], [form]; Hackathon Mongolia itself has no registration and needs none |
| Main organizers | [co-organizer] and Anar |
| Teams | logistics, finance, marketing, operations |
| Prizes | cash pool for the top three, 50 / 30 / 20; public floor 5,000,000 MNT, internal target 15,000,000; final size announced Nov 16; each of five track winners gets 2,000,000 MNT from the track sponsorship |
| Venue budget | 20,000,000 MNT for two days including overnight, unless a venue partner gives the hall in kind |
| Wifi | provided by the venue; confirm capacity for 350 devices at the walk-through |

Open, with owner and date

| Decision | Owner | By |
| --- | --- | --- |
| Visual identity: logo, colors, shirt design | marketing | Oct 9 |
| Venue, including overnight permission and two sleeping rooms | logistics + co-organizer | Nov 4 gate |
| Who owns program and judging (the hackathon-specific work: problem bank, submission platform, mentors, judging) | Anar, within operations | Oct 8 |
| Submission platform: Devpost vs own form | operations | Oct 20 |
| Final prize pool size above the 5M floor, set by what sponsors commit; announced Nov 16 | finance | Nov 15 |
| Night-shift adults: 6 needed for 220 | operations + adult lead | Nov 17 gate |
| Merch quotes: shirts, stickers, badges; merch sponsor or budget line | marketing | Oct 17 |

## 3. Organizing structure

Two organizations, two main organizers, four teams. Hackathon Mongolia owns everything about the program and the participants. Uram Enerel owns everything that needs a legal entity: contracts, bank account, receipts, government letters, plus the school-chapter outreach and health-side judges. Two main organizers decide; four teams execute. MUN organizing covers most of this well: registration, venue, delegates, food, sponsors, ceremonies. The parts a MUN does not have are the problem statements, the submission platform, mentors, judging logistics and the overnight. Those sit in operations under one named owner who has done a hackathon.

| Team | Owns | Lead |
| --- | --- | --- |
| Main organizers | gates, partners, sponsor meetings (co-organizer), documents and program (Anar), stage | [co-organizer], Anar |
| Logistics | venue contract and walk-through, tables and power for 55 teams, wifi with the telecom sponsor, signage, supplies, catering quotes and orders, delivery timing, sleeping rooms, security, cleanup | [name] |
| Finance | money flow through Uram Enerel, sponsor contracts and invoices, budget, ledger with receipts, prizes and prize tax, post-event financial report; works directly with Uram Enerel's accountant | [name] |
| Marketing | name and identity, website or Facebook event, registration form, school and university outreach, group chat, info emails, social posts, media, photographer, results post | [name] |
| Operations | run-of-show, check-in, track board, submission platform, mentors, judges and rubric, workshops, volunteer roster, night shift, consent forms, safety, judging tally | [name] |
| Adult lead | signs venue and sponsor documents with the NGO, responsible on site 24 hours, on call overnight | [name] |

Weekly rhythm. One 30-minute all-hands on Sunday evening (Oct 11, 18, 25, Nov 1, 8, 15, 22) with the gate status; team leads post a three-line update in the organizer chat every Wednesday. Decisions not made in those two places are made by the main organizers the same day.

Headcount for the event itself: 2 main organizers, 4 team leads, ~10 more organizers and volunteers for check-in, floor, food and timekeeping; adult lead plus 5 night-shift adults; 20 mentors; 18 judges; 1 first aider; 1 photographer. About 60 people serving 220.

## 4. Timeline, Oct 7 → Dec 1

Owners: M main organizers · L logistics · F finance · K marketing · O operations · A adult lead.

### Week 1 · Oct 7–13 · venue, sponsors, registration

| Date | Task | Owner |
| --- | --- | --- |
| Wed Oct 7 | Read the three documents. Agree the theme and tracks. Assign team leads. | M |
| Thu Oct 8 | Name the program-and-judging owner. Venue shortlist: three candidates with overnight capacity for 220. NGO letter to the first venue. | M, L |
| Fri Oct 9 | Sponsor proposal final; event name chosen; sponsor target list of 30 companies sorted by tier fit. First 15 sponsor emails sent. | K, F, co-organizer |
| Sat Oct 10 | Registration form, group chat, Facebook event or site ready. Venue walk-throughs booked. | K, L |
| Sun Oct 11 | Publish rules, tracks and problem bank on the site. All-hands 1. | O, M |
| Tue Oct 13 | Sponsor follow-up calls to the first 15; second wave of 15 emails. | co-organizer, F |

### Week 2 · Oct 14–20 · venue gate, people

| Date | Task | Owner |
| --- | --- | --- |
| Wed Oct 14 | Venue gate. Written confirmation with overnight access and two sleeping rooms, or switch to the second candidate today; daytime-only yes means Plan B. | M, L |
| Thu Oct 15 | Telecom sponsor ask for wifi and a backup line, with the venue's floor plan. | L, co-organizer |
| Fri Oct 16 | Ask 30 potential mentors and 25 potential judges, three per track plus reserves. Send the judge brief. | O |
| Sat Oct 17 | Two catering quotes for 260 people, five meals and snacks. School and university outreach: Uram Care's 15+ school chapters first, then 25 institutions with one teacher or club contact each. | L, K |
| Sat Oct 17 | Registration opens. Announcement on the website and social media; organizers share it in their own networks. | K, M |
| Sun Oct 18 | Gold track sponsors confirmed so far receive the optional-challenge invite. | F, O |
| Sun Oct 18 | All-hands 2. Registration check after day one: 40+ on track. | M |
| Tue Oct 20 | Submission platform decided and set up; dummy submission tested. | O |

### Week 3 · Oct 21–24 · program

| Date | Task | Owner |
| --- | --- | --- |
| Wed Oct 21 | Sponsor follow-ups; third wave to in-kind targets: printing, water, swag, photographer. | co-organizer, K |
| Thu Oct 22 | Workshop speakers confirmed; mentor roster by track. | O |
| Fri Oct 23 | Consent form final (overnight section), translated, published. | O |
| Sat Oct 24 | Registration check: 150+ on track; waitlist logic ready at 300. | K |

### Weeks 4–6 · Oct 25–Nov 14 · more sponsors, venue (added when the event moved to Nov 28–29)

| Date | Task | Owner |
| --- | --- | --- |
| Oct 25 to Nov 14 | Sponsor calls and meetings continue; in-kind asks for the venue and food first. All-hands every Sunday: Oct 25, Nov 1, Nov 8. | F, co-organizer, M |
| Wed Nov 4 | Venue gate (moved). Written confirmation with overnight access and two sleeping rooms, or switch to the next candidate; daytime-only yes means Plan B. | M, L |
| Sat Nov 14 | GDG Ulaanbaatar's DevFest UB: Touch Grass volunteers help; ask for a short slot or a table to recruit participants and mentors. | K, M |

### Week 7 · Nov 15–17 · money gate

| Date | Task | Owner |
| --- | --- | --- |
| Sun Nov 15 | Money gate. Sponsor commitments close. Budget final. Prize plan final. Contracts out from the NGO. | F, M |
| Sun Nov 15 | All-hands 3, same evening as the money gate. | M |
| Tue Nov 17 | Night-shift gate. Adult lead plus five night adults confirmed, or switch to Plan B. Security and first aider booked. | O, A, L |

### Week 8 · Nov 18–24 · lock everything

| Date | Task | Owner |
| --- | --- | --- |
| Wed Nov 18 | Info email 1 to registrants. Track sponsors' optional challenges final. | K, O |
| Thu Nov 19 | Buy supplies: 60 power strips, 20 extension cords, tape, name tags, first aid, flashlights, sign-out log. Order printing. | L |
| Fri Nov 20 | Judges and mentors confirmed: 18 and 20. Briefing invitation for Nov 27 sent. | O |
| Sat Nov 21 | Sponsor logos collected; signage and website updated; sponsor deliverables checklist started. | K, F |
| Sun Nov 22 | Reconfirmation message to all registrants: reply to keep your seat. All-hands 4. | K, M |
| Mon Nov 23 | Food ordered for reconfirmed count plus 10 percent, with dietary needs and overnight count. All-hands 4. | L, M |
| Tue Nov 24 | Registration closes. Headcount gate. Fill from waitlist; final count to venue, caterer and security. | K, L |

### Week 9 · Nov 25–29 · event

| Date | Task | Owner |
| --- | --- | --- |
| Wed Nov 25 | Info email 2: schedule, rules, consent reminder, what to bring for the overnight. Consent upload deadline. | K, O |
| Thu Nov 26 | Print check-in lists, judge sheets, table numbers, track board. Pack supplies. MC script final. | O, L, M |
| Fri Nov 27 | Briefings: volunteers, judges, mentors, night shift, sponsor speakers. Venue setup in the evening. | M, O, L |
| Sat Nov 28 | Event day 1. | all |
| Sun Nov 29 | Submissions 13:00, judging, finals, awards 16:20, close 17:00, venue back 18:30. | all |

### After

| Date | Task | Owner |
| --- | --- | --- |
| Mon Nov 30 | Thank-you emails with photos and numbers to sponsors, partners, judges, mentors, venue. Results post. | M, K |
| Tue Dec 1 | Survey out. Metrics sheet filled. Ledger closed by the NGO. | K, F |
| Fri Dec 4 | Written report delivered to every sponsor. Team retro. | F, M |

## 5. Budget (MNT)

Cash flows only through Uram Enerel NGO. Figures below use the organizers' estimates: venue 20M for two days, food 10M, staff 3M. The prize pool is planned at its 15M target; the public commitment is 5M and up. Merchandise and supplies are estimates for Ulaanbaatar print shops and markets; get two quotes each by Oct 17.

| Line | Amount | Note |
| --- | --- | --- |
| Venue, two days including overnight | 20,000,000 | estimate; zero if a venue partner gives the hall in kind |
| Cash prize pool, top three, 50 / 30 / 20 | 15,000,000 target; 5,000,000 floor | at the target 7.5M / 4.5M / 3M; at the floor 2.5M / 1.5M / 1M; 5% personal income tax withheld by Uram Enerel on payout |
| Track prizes, five winners × 2,000,000 | 10,000,000 | paid by the five Gold sponsors, 2,000,000 each; an unsold track's prize comes from the general budget |
| Food, five meals and snacks for 220 participants and 45 staff | 10,000,000 | about 37,700 per person over 24 hours; tight, so boxed lunches and a hot dinner, and ask the food sponsor for catering in kind to top it up |
| Judges, designers, finance support | 3,000,000 | honoraria and design work; judges from sponsors cost nothing |
| T-shirts, 220 | 3,300,000 | one-colour print on a plain tee runs about 12,000–18,000 each at 200+; two-colour or heavier cotton 20,000+ |
| Stickers, badges, lanyards | 1,100,000 | 500 die-cut stickers about 500,000; 300 badges with lanyards about 600,000 |
| Power strips 60, extension cords 20, tape, name tags, first aid, flashlights | 2,500,000 |  |
| Photography and video | 800,000 | one photographer both days plus a 2-minute recap video |
| Overnight security and cleaning | 800,000 |  |
| Printing and signage | 700,000 | posters, table numbers, track board, judge sheets, certificates |
| First aider, 24 hours | 300,000 |  |
| Wifi | 0 | provided by the venue |
| Subtotal | 67,500,000 |  |
| Contingency 10% | 6,750,000 |  |
| Total | 74,250,000 at the prize target; 63,250,000 at the floor | about 20,000,000 less if the venue is in kind |

Scaling: 180 attending saves about 900,000 on shirts and badges and nothing else; 260 adds about 1,200,000. Venue and prizes are fixed, so headcount barely moves this budget. What moves it is whether the hall is paid or given.

Income plan

| Source | Amount | Notes |
| --- | --- | --- |
| Platinum sponsors | 25,000,000 to 30,000,000 | five or six × 5,000,000 or more; covers the venue and the top-three pool; a venue giving the hall in kind counts as Platinum |
| Gold track sponsors | 10,000,000 | five × 2,000,000; each pays its own track's prize |
| Silver sponsors | food in kind plus 1,000,000 to 2,000,000 each | catering, shirts, printing, devices, media |
| Participation fees | about 9,900,000 | 45,000 × about 220 |
| Cash target | 68,000,000 with a paid venue and the 15M prize target; 48,000,000 with the hall in kind |  |

Cash timing matters more than the total: the venue wants a deposit before sponsor money arrives. Ask a Platinum sponsor to pay the venue directly, or have the NGO bridge the deposit against signed contracts.

Minimum viable version if the money gate fails on Nov 15: prize pool stays at the 5M floor, shirts cut, venue partner in kind or Plan B at a free university hall, sponsors pay the caterer directly. Cash needed then: about 15,000,000.

Rules for money. Every payment from Uram Enerel's account with an e-barimt. Sponsorship invoiced as advertising services under Advertising Law article 19. Cash prizes carry 5 percent personal income tax withheld by the NGO. One ledger sheet, shared with sponsors in the report.

## 6. Risks and fallbacks

| Risk | Fallback |
| --- | --- |
| No venue allows 220 people overnight | Plan B daytime split, written into the agenda; or split sleeping across two rooms in a university building with security |
| Wifi collapses at 300 devices | telecom sponsor provides enterprise wifi plus a backup line; participants told to bring hotspots as last resort |
| Power: 55 tables of laptops trip the circuits | electrician check at the walk-through; strips spread across circuits; phones charged at a separate station |
| Under 150 registrations by Oct 24 | double outreach to universities; sponsors told honestly; budget scaled |
| Over 300 registrations | waitlist; second venue room if available; never exceed fire capacity |
| Judging overruns with 55 teams | track panels, 5-minute slots, timekeepers, finals capped at 8 |
| Projects overlap | broad tracks, no problem list, teams bring their own ideas; rubric rewards solving a real problem |
| A minor is hurt, ill or leaves at night | consent forms with emergency contacts, sign-out log, two adults awake per 100, first aider on site, parent numbers at the desk |
| Sponsor demands control of judging | tier table and contract say one judge seat, rubric decides |
| A sponsor pays late | contract payment dates before Nov 22; food sponsor pays caterer directly |
| Venue deposit due before sponsor cash lands | a Platinum sponsor pays the venue directly, or the NGO bridges the deposit against signed contracts |
| Sponsors commit less than the 15M prize target | the public promise is 5M and up with a 50 / 30 / 20 split, so nothing has to be retracted; publish the final size on Nov 16 |
| Team burnout: 31 days, exams | two leads per team where possible; the Sunday all-hands is the only mandatory meeting |

## 7. Registration, consent, rules

Registration form fields. Name, school or university, grade or year, date of birth, email, phone, parent or guardian name and phone for under-18s, dietary needs, skills (multi-select), experience level, team or solo, laptop yes/no, staying overnight yes/no, I have read the rules, consent form will be uploaded by Nov 25 or brought signed. Optional: how you heard about us, CV share opt-in for sponsors.

Confirmation email. Registered; seat confirmed after reconfirmation Nov 22 to 24; under-18 consent link; group chat link; questions contact.

Consent form. Participation, overnight choice (stay, or leave at 21:00 and return by 10:00), pickup Sunday 17:00, emergency contact and medical notes, rules acknowledged, photo release, project publication consent, data deletion within a month. Translated to Mongolian; adult lead holds the forms during the event.

Publish on the site by Oct 11: rules, code of conduct, tracks and problem bank, rubric, agenda, consent form, FAQ.

## 8. Event days, summary

Full minute-by-minute agenda is in the companion document. The shape:

- Saturday: setup 10:00, doors 11:00, opening 12:00, team formation and track board 12:30, hacking 13:00, lunch at tables, workshop 14:30, mentor hour 16:00, workshop 17:30, dinner 19:00, mini-event 20:30, minor sign-out 21:00, night briefing 22:00, midnight snack 23:30.

- Overnight: quiet hours 01:00 to 06:00, two adults awake per 100 participants, floor walk every 30 minutes, breakfast 07:00.

- Sunday: returnees by 10:00, judges 11:00, lunch 12:15, submissions 13:00, track judging 13:30 to 15:00, finals 15:15, awards 16:20, close 17:00, venue back 18:30.

Day-of checklists, short form

- Setup: 55 tables with 4 chairs, power strip on every table, cords taped, wifi name on every table card, projector with the countdown clock, check-in desk with four lines, signs, snack station, lockable supply room, two sleeping rooms labeled, security briefed.

- Check-in: name on list, consent on file or handed over, overnight tag, dietary tag, wristband, point to chat and schedule, late list until 13:30, headcount to logistics at 12:30.

- Food: lunch boxes at tables 13:00, dinner 18:45, midnight snack 23:15, breakfast 06:45, Sunday lunch 12:15; dietary meals labeled; volunteers serve.

- Overnight: sign-out log from 21:00, roster at the desk, floor walks logged, parent list and consent forms at the desk, sleeping rooms cleared by 09:30.

- Judging: score sheets per panel with table lists, timekeeper per panel, two-person tally, finalists posted in the chat, prize envelopes or products in order on the stage table, certificates filled during finals.

- Closing: group photo with sponsor boards in frame, survey on screen, adult lead at the door, lost-and-found sweep, room photographed as returned.

## 9. After the event

Within 24 hours: thank-yous with photos and numbers; results post with project links. Within 48 hours: survey out; metrics sheet filled; ledger closed. By December 4: report to every sponsor and partner with participants, institutions, teams, projects, finalists, winners, media, survey results, and the itemized ledger; retro with the four team leads; a date and a venue ask for 2027.