# Touch Grass — Timeline

## Thursday October 8 to Friday November 13, 2026

Generated October 8, 2026. 30 days to the event. Owners: M main organizers · L logistics · F finance · K marketing · O operations · A adult lead · UE Uram Enerel. Companion to the master plan; where they differ, this file is the newer one.

## Gates

A gate is a date where the plan changes shape if the condition is not met. Four of them.

| Gate | Date | Pass condition | If missed |
| --- | --- | --- | --- |
| Venue | Wed Oct 14 | written yes with overnight access and two sleeping rooms | switch to the next candidate the same day; daytime-only yes means Plan B |
| Money | Sun Oct 25 | sponsor commitments cover venue, food and the 5M prize floor | run the minimum version: prize pool at the floor, no shirts, hall in kind or Plan B, sponsors pay the caterer directly |
| Night shift | Tue Oct 27 | adult lead plus five adults confirmed for overnight shifts | drop the overnight, run Plan B |
| Headcount | Tue Nov 3 | 150+ reconfirmed | merge tables, cut one meal order, keep the event |

## Weekly rhythm

All-hands every Sunday evening for 30 minutes: Oct 11, 18, 25, Nov 1. Team leads post a three-line update in the organizer chat every Wednesday. Decisions not made in those two places are made by the main organizers the same day.

## Day by day

| Date | Owner | Task |  |
| --- | --- | --- | --- |
| Thu Oct 8 | M | Name the four team leads and the program-and-judging owner (Anar). Share the three documents with every lead. |  |
| Thu Oct 8 | L | Venue shortlist: three candidates with overnight capacity for 220, two sleeping rooms, wifi for 350 devices. Uram Enerel sends the request letter to candidate one. |  |
| Thu Oct 8 | K | Brief the designer: Touch Grass logo, colors, shirt front and back, poster. |  |
| Fri Oct 9 | M | Co-organizer sends the first 15 sponsor emails with the proposal attached. |  |
| Fri Oct 9 | L | Book walk-throughs at all three venue candidates for Oct 12–13. |  |
| Fri Oct 9 | F | Sponsor target sheet: 30 companies sorted by tier fit, with contact, date asked, status columns. |  |
| Sat Oct 10 | K | Build and test the registration form; open the group chat; draft the Facebook event or site. |  |
| Sat Oct 10 | O | Draft the rules, problem bank, rubric, agenda and FAQ pages from the theme document. |  |
| Sun Oct 11 | M | All-hands 1, 30 minutes: gate status, outreach plan, who is calling which sponsor. | all-hands |
| Sun Oct 11 | O | Publish rules, tracks, problem bank, rubric, agenda, consent-form notice and FAQ. |  |
| Mon Oct 12 | M | Co-organizer phones the first 15 sponsors. |  |
| Tue Oct 13 | L | Venue walk-throughs: count outlets, wifi speed test with 5 devices, sleeping rooms, security, who unlocks and locks, food service area. Photograph everything. |  |
| Tue Oct 13 | F | Sponsor wave 2: 15 more emails. |  |
| Wed Oct 14 | M | VENUE GATE: written confirmation with overnight access and two sleeping rooms, or switch to candidate two today. Daytime-only yes means Plan B. | GATE |
| Thu Oct 15 | L | Venue confirms wifi capacity for 350 devices in writing; electrician check scheduled for Nov 6. |  |
| Thu Oct 15 | UE | Sponsorship contract template and invoice format ready: advertising services, e-barimt, payment date, refund clause. |  |
| Fri Oct 16 | K | Outreach prep: line up personal and youth-community networks to share the link on Oct 17; post a teaser. |  |
| Fri Oct 16 | O | Ask 30 mentors and 25 judges, three judges per track plus reserves, with the one-page brief and the Nov 6 briefing date. |  |
| Sat Oct 17 | L | Two catering quotes for 260 people: five meals and snacks, dietary options, delivery times. |  |
| Sat Oct 17 | K | Two merchandise quotes: 220 shirts, 500 stickers, 300 badges with lanyards. |  |
| Sat Oct 17 | K | Registration opens. Announcement on the website and social media; every organizer shares the link in their own networks. | milestone |
| Sun Oct 18 | M | All-hands 2. Registration check after day one: 40+ means on track; under 20 means double outreach this week. | all-hands |
| Sun Oct 18 | O | Invite confirmed track sponsors to set an optional challenge for their track. |  |
| Mon Oct 19 | F | Phone follow-ups on sponsor waves 1 and 2; update the sheet. |  |
| Mon Oct 19 | K | Three-week content calendar: two posts a week, one countdown post, sponsor announcements as they land. |  |
| Mon Oct 19 | O | Ask the two workshop speakers: data sources, and how to demo. |  |
| Tue Oct 20 | L | Security, cleaning and first-aider quotes; provisional bookings. |  |
| Tue Oct 20 | O | Submission platform decided and set up; one dummy submission tested end to end. |  |
| Wed Oct 21 | K | Sponsor wave 3, in kind: printing, water and snacks, photographer, merchandise. |  |
| Thu Oct 22 | O | Workshop speakers confirmed; mentor roster by track, version 1. |  |
| Fri Oct 23 | O | Consent form final with the overnight section, translated to Mongolian, linked from the confirmation email. |  |
| Sat Oct 24 | L | Table and chair count confirmed with the venue: 55 tables, 220 chairs, stage, projector, sound. |  |
| Sat Oct 24 | K | Registration check: 150+ on track. Waitlist logic live at 300. |  |
| Sun Oct 25 | M | MONEY GATE: sponsor commitments close. Budget final. Prize pool size set above the 5M floor. All-hands 3. | GATE |
| Sun Oct 25 | UE | Contracts sent to every committed sponsor, payment dates on or before Nov 1. |  |
| Mon Oct 26 | F | Venue deposit arranged: a Platinum sponsor pays the venue directly, or Uram Enerel bridges against signed contracts. |  |
| Mon Oct 26 | K | Announce the final prize pool size. Request logos and 40-word descriptions from every sponsor. |  |
| Tue Oct 27 | L | Security, cleaning and first aider booked firm for Nov 7–8. |  |
| Tue Oct 27 | O | NIGHT-SHIFT GATE: adult lead plus five night adults confirmed with shifts, or switch to Plan B. | GATE |
| Wed Oct 28 | K | Info email 1 to registrants: venue, overnight rules, what to bring, consent form, schedule outline. |  |
| Wed Oct 28 | O | Track sponsors' optional challenges final and published; track board layout done. |  |
| Thu Oct 29 | L | Buy supplies: 60 power strips, 20 extension cords, gaffer tape, name tags, first-aid kits, flashlights, sign-out log. Order printing and signage. |  |
| Fri Oct 30 | O | Judges (18) and mentors (20) confirmed; sponsors' judges and workshop speakers named; Nov 6 briefing invitations sent. | milestone |
| Sat Oct 31 | F | Sponsor deliverables checklist opened: what each sponsor is owed, when, done or not. |  |
| Sat Oct 31 | K | Sponsor logos on the site; signage files to the printer; shirt order placed if the merchandise sponsor is confirmed. |  |
| Sun Nov 1 | M | All-hands 4: run-of-show read-through, roles on the day, open risks. | all-hands |
| Sun Nov 1 | K | Reconfirmation message to all registrants: reply YES by Nov 3, 20:00. |  |
| Mon Nov 2 | L | FOOD ORDERED for the reconfirmed count plus 10 percent, with dietary needs and the overnight count. | milestone |
| Mon Nov 2 | F | Confirm sponsor payments received; venue deposit paid; prize money ring-fenced. |  |
| Tue Nov 3 | K | HEADCOUNT GATE: registration closes. Waitlist filled. Final count to venue, caterer, security. | GATE |
| Wed Nov 4 | K | Info email 2: full schedule, rules, submission link, consent reminder, overnight packing list, pickup rule. |  |
| Wed Nov 4 | O | Consent upload deadline. Volunteer roster (10) and night-shift roster final. |  |
| Thu Nov 5 | L | Pack supplies; confirm delivery times with the caterer; confirm security and first aider arrival times. |  |
| Thu Nov 5 | O | Print check-in lists, judge score sheets, table numbers, track board, certificates. MC script final. Sponsor opening slides collected. |  |
| Fri Nov 6 | M | Briefings, 30 minutes each: volunteers, judges, mentors, night shift, sponsor speakers. |  |
| Fri Nov 6 | L | Venue setup in the evening: tables, power strips taped, signage, check-in desk, sleeping rooms, projector and wifi test, electrician check. |  |
| Sat Nov 7 | M | EVENT DAY 1. Organizers 12:00, doors 13:00, opening 14:00, hacking 15:00, dinner 19:00, minor sign-out 21:00, night shift from 22:00. | EVENT |
| Sun Nov 8 | M | EVENT DAY 2. Breakfast 07:00, judges 13:00, submissions 15:00, track judging 15:30, finals 17:15, awards 18:20, close 19:00, venue back 20:30. | EVENT |
| Mon Nov 9 | K | Thank-you emails with photos and numbers to sponsors, partners, judges, mentors, venue. Results post with project links, with team permission. |  |
| Tue Nov 10 | K | Feedback survey out. Metrics sheet filled. |  |
| Tue Nov 10 | UE | Ledger closed: every payment with its e-barimt; prize payouts made with 5 percent tax withheld. |  |
| Wed Nov 11 | K | Photos and recap video delivered; report drafting starts. |  |
| Thu Nov 12 | M | Report reviewed by Uram Enerel and both main organizers. |  |
| Fri Nov 13 | F | Report delivered to every sponsor and partner. Team retro. 2027 date and venue ask pencilled. | milestone |

## By team

Each lead reads only their list. Dates in bold are gates the team owns.

### Main organizers (M)

- Thu Oct 8: Name the four team leads and the program-and-judging owner (Anar). Share the three documents with every lead.

- Fri Oct 9: Co-organizer sends the first 15 sponsor emails with the proposal attached.

- Sun Oct 11: All-hands 1, 30 minutes: gate status, outreach plan, who is calling which sponsor.

- Mon Oct 12: Co-organizer phones the first 15 sponsors.

- Wed Oct 14: VENUE GATE: written confirmation with overnight access and two sleeping rooms, or switch to candidate two today. Daytime-only yes means Plan B.

- Sun Oct 18: All-hands 2. Registration check after day one: 40+ means on track; under 20 means double outreach this week.

- Sun Oct 25: MONEY GATE: sponsor commitments close. Budget final. Prize pool size set above the 5M floor. All-hands 3.

- Sun Nov 1: All-hands 4: run-of-show read-through, roles on the day, open risks.

- Fri Nov 6: Briefings, 30 minutes each: volunteers, judges, mentors, night shift, sponsor speakers.

- Sat Nov 7: EVENT DAY 1. Organizers 12:00, doors 13:00, opening 14:00, hacking 15:00, dinner 19:00, minor sign-out 21:00, night shift from 22:00.

- Sun Nov 8: EVENT DAY 2. Breakfast 07:00, judges 13:00, submissions 15:00, track judging 15:30, finals 17:15, awards 18:20, close 19:00, venue back 20:30.

- Thu Nov 12: Report reviewed by Uram Enerel and both main organizers.

### Logistics (L)

- Thu Oct 8: Venue shortlist: three candidates with overnight capacity for 220, two sleeping rooms, wifi for 350 devices. Uram Enerel sends the request letter to candidate one.

- Fri Oct 9: Book walk-throughs at all three venue candidates for Oct 12–13.

- Tue Oct 13: Venue walk-throughs: count outlets, wifi speed test with 5 devices, sleeping rooms, security, who unlocks and locks, food service area. Photograph everything.

- Thu Oct 15: Venue confirms wifi capacity for 350 devices in writing; electrician check scheduled for Nov 6.

- Sat Oct 17: Two catering quotes for 260 people: five meals and snacks, dietary options, delivery times.

- Tue Oct 20: Security, cleaning and first-aider quotes; provisional bookings.

- Sat Oct 24: Table and chair count confirmed with the venue: 55 tables, 220 chairs, stage, projector, sound.

- Tue Oct 27: Security, cleaning and first aider booked firm for Nov 7–8.

- Thu Oct 29: Buy supplies: 60 power strips, 20 extension cords, gaffer tape, name tags, first-aid kits, flashlights, sign-out log. Order printing and signage.

- Mon Nov 2: FOOD ORDERED for the reconfirmed count plus 10 percent, with dietary needs and the overnight count.

- Thu Nov 5: Pack supplies; confirm delivery times with the caterer; confirm security and first aider arrival times.

- Fri Nov 6: Venue setup in the evening: tables, power strips taped, signage, check-in desk, sleeping rooms, projector and wifi test, electrician check.

### Finance (F)

- Fri Oct 9: Sponsor target sheet: 30 companies sorted by tier fit, with contact, date asked, status columns.

- Tue Oct 13: Sponsor wave 2: 15 more emails.

- Mon Oct 19: Phone follow-ups on sponsor waves 1 and 2; update the sheet.

- Mon Oct 26: Venue deposit arranged: a Platinum sponsor pays the venue directly, or Uram Enerel bridges against signed contracts.

- Sat Oct 31: Sponsor deliverables checklist opened: what each sponsor is owed, when, done or not.

- Mon Nov 2: Confirm sponsor payments received; venue deposit paid; prize money ring-fenced.

- Fri Nov 13: Report delivered to every sponsor and partner. Team retro. 2027 date and venue ask pencilled.

### Marketing (K)

- Thu Oct 8: Brief the designer: Touch Grass logo, colors, shirt front and back, poster.

- Sat Oct 10: Build and test the registration form; open the group chat; draft the Facebook event or site.

- Fri Oct 16: Outreach prep: line up personal and youth-community networks to share the link on Oct 17; post a teaser.

- Sat Oct 17: Registration opens. Announcement on the website and social media; every organizer shares the link in their own networks.

- Sat Oct 17: Two merchandise quotes: 220 shirts, 500 stickers, 300 badges with lanyards.

- Mon Oct 19: Three-week content calendar: two posts a week, one countdown post, sponsor announcements as they land.

- Wed Oct 21: Sponsor wave 3, in kind: printing, water and snacks, photographer, merchandise.

- Sat Oct 24: Registration check: 150+ on track. Waitlist logic live at 300.

- Mon Oct 26: Announce the final prize pool size. Request logos and 40-word descriptions from every sponsor.

- Wed Oct 28: Info email 1 to registrants: venue, overnight rules, what to bring, consent form, schedule outline.

- Sat Oct 31: Sponsor logos on the site; signage files to the printer; shirt order placed if the merchandise sponsor is confirmed.

- Sun Nov 1: Reconfirmation message to all registrants: reply YES by Nov 3, 20:00.

- Tue Nov 3: HEADCOUNT GATE: registration closes. Waitlist filled. Final count to venue, caterer, security.

- Wed Nov 4: Info email 2: full schedule, rules, submission link, consent reminder, overnight packing list, pickup rule.

- Mon Nov 9: Thank-you emails with photos and numbers to sponsors, partners, judges, mentors, venue. Results post with project links, with team permission.

- Tue Nov 10: Feedback survey out. Metrics sheet filled.

- Wed Nov 11: Photos and recap video delivered; report drafting starts.

### Operations (O)

- Sat Oct 10: Draft the rules, problem bank, rubric, agenda and FAQ pages from the theme document.

- Sun Oct 11: Publish rules, tracks, problem bank, rubric, agenda, consent-form notice and FAQ.

- Fri Oct 16: Ask 30 mentors and 25 judges, three judges per track plus reserves, with the one-page brief and the Nov 6 briefing date.

- Sun Oct 18: Invite confirmed track sponsors to set an optional challenge for their track.

- Mon Oct 19: Ask the two workshop speakers: data sources, and how to demo.

- Tue Oct 20: Submission platform decided and set up; one dummy submission tested end to end.

- Thu Oct 22: Workshop speakers confirmed; mentor roster by track, version 1.

- Fri Oct 23: Consent form final with the overnight section, translated to Mongolian, linked from the confirmation email.

- Tue Oct 27: NIGHT-SHIFT GATE: adult lead plus five night adults confirmed with shifts, or switch to Plan B.

- Wed Oct 28: Track sponsors' optional challenges final and published; track board layout done.

- Fri Oct 30: Judges (18) and mentors (20) confirmed; sponsors' judges and workshop speakers named; Nov 6 briefing invitations sent.

- Wed Nov 4: Consent upload deadline. Volunteer roster (10) and night-shift roster final.

- Thu Nov 5: Print check-in lists, judge score sheets, table numbers, track board, certificates. MC script final. Sponsor opening slides collected.

### Uram Enerel (UE)

- Thu Oct 15: Sponsorship contract template and invoice format ready: advertising services, e-barimt, payment date, refund clause.

- Sun Oct 25: Contracts sent to every committed sponsor, payment dates on or before Nov 1.

- Tue Nov 10: Ledger closed: every payment with its e-barimt; prize payouts made with 5 percent tax withheld.

### Adult lead (A)

- Thu Oct 8 to Wed Oct 14: sign the venue request and, once chosen, the venue agreement with Uram Enerel.

- By Sun Oct 25: sign sponsorship contracts alongside Uram Enerel where the venue or sponsor asks for a named responsible adult.

- Tue Oct 27: confirm the five night-shift adults and the shift plan with operations.

- Fri Nov 6: attend the night-shift briefing.

- Sat Nov 7 12:00 to Sun Nov 8 19:30: on site throughout; at the door for the 21:00 sign-out and the 19:00 pickups; on call all night.

## Event days, the short version

| Saturday Nov 7 |  | Sunday Nov 8 |  |
| --- | --- | --- | --- |
| 12:00 | setup | 07:00 | breakfast |
| 13:00 | doors, check-in | 09:00 | day shift; sleeping rooms cleared by 09:30 |
| 14:00 | opening | 10:00 | returnees back |
| 14:30 | team formation, track board | 12:00 | three-hour check; lunch at tables 12:15 |
| 15:00 | hacking starts, lunch at tables | 13:00 | judges arrive and brief |
| 16:30 | workshop 1 | 15:00 | submission deadline |
| 18:00 | mentor hour | 15:30 | track judging at tables |
| 19:00 | dinner | 17:00 | tally, eight finalists |
| 19:45 | workshop 2 | 17:15 | finals on stage |
| 21:00 | sign-out for minors going home | 18:20 | awards |
| 22:00 | night shift begins | 19:00 | close |
| 23:30 | midnight snack; quiet hours 01:00–06:00 | 20:30 | venue handed back |

Full minute-by-minute agenda: the theme document, section 6.